## Slide 1
Vision and Case for Change
A guide

## Slide 2
Document purpose
What is a Vision and Case for Change? | A Vision Statement is a clear and concise message of what the programme or project will achieve and what the future state will be, following programme/project delivery. The Case for Change is a key tool that provides information on the rationale for change; it articulates the current state, why this needs to change and what the future state will look like to support a programme or project to deliver its vision.
Why do we need a Vision and Case for Change? | Vision A clear vision statement is a critical requirement to make change in any major transformation programme or project, a smooth, coherent and holistic process. It: Gives a sense of the future Guides decision making and strategy Creates a shared purpose Creates buy in and drives momentum. Case for Change It is also important that all stakeholders are fully aware of the reasons the current state must be changed. Developing a shared understanding of the drivers for change and the benefits to be achieved will help to: Increase buy-in for the change Harness resources required to make the change happen Minimise resistance Anticipate questions and concerns Generate interest and dialogue about the changes.
Who is the Vision and Case for Change for? | The Vision and Case for Change contains messages that are relevant for: Internal recipients of change (the MDAs) External recipients of change (e.g., Organisational Partners or other third-party stakeholders).

## Slide 3
Overview
  Every individual has a basic human need to feel they are part of something purposeful. People don’t buy what you do or how you do it but why you do it. Creating a compelling and clear purpose, vision, and case for change narrative helps to consistently drive understanding and gain support for the change. Your workshop is to drive out the “why” clearly and to be a powerful and simple way to communicate your purpose.
  Background reading:
  Prior to identifying the “Case for Change,” take into account the following:
  Review the business case, benefits, and any materials that were used to promote, and gain the approval of the project or initiative.
  Circulate the Project Charter to attendees.
  Identify specific questions around the desired future state that will be asked during the session.
Workshop attendees:
Project Executive Sponsor
Steering Committee Members
Project/Workstream Team Leads

## Slide 4
Case for change
The case for change provides a clear story about the purpose and intended outcomes of our path to the future
Components of the “case for change”
Why are we going through these changes?
What are we going to achieve?
How will we get there?
What does it mean for employees? What’s in it for me?
1
2
3
4
The “Why”
The “What”
The “How”
The “Who”
Together these components enable leaders across the organisation to share one clear and consistent message about the project

## Slide 5
Workshop considerations
As a team :
Determine the need for the project and why future-state changes are necessary
Articulate what will change and who will be impacted
Describe how the MDA will implement the proposed changes (the solution) and the expected timing of the changes
Highlight the benefits that are expected as a result of the changes (business case)
List the consequences of delaying these changes.
What key elements jump out from the above session? Are there certain words that jump out? Using either a virtual whiteboard or sticky notes in a room or perhaps the chat room of your collaboration tool, get the team to put down words that help them articulate the journey of the transformation and what the future objectives will provide.
The facilitator supports bringing the team’s suggestions into a rough draft vision statement.
Finally, as a team develop a creative and visual picture of the vision – this will help employees to visualise and remember the “why” - A picture tells a thousand words. To do this, imagine your team are on the new road to this destination – what has changed to make your journey easier? And what do you notice? Describe it to each other.
Identify pain points that will be mitigated by the project and business drivers
Identify key benefits that the project will enable
Understand potential challenges to deployment and sustainment of changes.
Key points to include

## Slide 6
Writing the vision statement
Find the core of your transformation
Grab people’s attention by surprising them
Make sure it can be grasped and remembered later
Give an idea believability
Help people see the importance of it
Empower people to use it through narrative
Simple
Unexpected
Concrete
Credible
Emotional
Stories

## Slide 7
Case for change (sample)
Vision: University (X) is transforming the way we serve our mission by putting you first. The Academic Division and Health System are joining forces. We aim to create a consistent and exceptional work experience for every University colleague – one that is commensurate with our reputation of excellence. | 
Current Challenges The case for transforming Human Resources (HR) at University has never been stronger. Outstanding HR services are crucial for the University to deliver on its mission and its strategic goals. Current University: Mass retirement of existing talent Increasingly competitive market for new talent Inconsistent service experience Systemic inefficiencies and redundancies 70+ disjoined systems that collect HR data and five different learning management systems across three entities. | The Solution Human Resources must be focused and unwavering in its support of excellence. We aim to provide the highest quality HR services to advance the University’s mission of world-class teaching, research, patient care, and public service. We commit to: A recruiting, hiring, and onboarding experience consistent with the reputation of the University Improved satisfaction through seamless, consistent, high-quality HR services, and experiences Proactive support and engagement from qualified HR professionals A more efficient operating model that frees up HR professional to focus on more value-added activities.

## Slide 8: CONTACT US
TIU_Jamaica
TIU_Jamaica
TIUJamaica
www.publicsectortransformation.gov.jm
letusknow@transformation.gov.jm
Transformation Implementation Unit
Public Sector Transformation