## Slide 1
Stakeholder Engagement and Communication Plan
Example:

## Slide 2: This document outlines the strategic approach being taken to engage XYZ’s key stakeholders.
Document purpose
This documents aims to:
  Describe the strategic stakeholder engagement and communication framework.
  Identify the communication approach, including the use of cascading communication and profiling of stakeholder groups.
  Identify and leverage existing channels of communication within XYZ.
  Define the ‘key messages’ required to gather commitment and buy-in from different groups of stakeholders.
Key audience of this document:
  XYZ’s Project Sponsor
  XYZ’s Change Management Lead
  XYZ’s Business Process Owners and Change Champions (as representatives)
  XYZ’s Project Communication Team
  XYZ’s Project Team
  XYZ’s Project Management Office (as the PMO)
This document is to be used:
  To define all aspects of stakeholder engagement including monitoring key issues/ concerns / perceptions, defining and communicating key messages and planning key engagement opportunities.

## Slide 3
Table of contents
No. | Topics | Pages
1 | Stakeholder analysis | 4 – 7
2 | Stakeholder engagement and communication strategy | 8 - 18
3 | Detailed stakeholder engagement and communication plan | 19 – 21
4 | Key messages for stakeholder engagement execution | 22 – 25
5 | Monthly calendar plan of group-wide stakeholder engagement and communication plan | 26 - 29

## Slide 4: Part 1
Stakeholder analysis

## Slide 5
Stakeholder analysis
Perm Secs
Cabinet members, etc.
HR
Trade Unions
Current and future process/system owners
Manager groups
Impacted groups
Employees
COMMITMENT AND ADVOCACY
Key sponsors and decision makers
Communication will be delivered through 1:1/group meetings/ involvement in key decisions
STRONG CONSULT AND ENGAGE
Teams / groups highly impacted by changes and/or have high level of influence
Communication may be delivered though detailed briefings/workshops/
meetings
ENGAGE AND INFORM
Teams / groups impacted by changes but have less influence
Communication may be delivered though core briefs/focus groups etc.
AWARENESS
Other groups that have an interest in the activities
Awareness may be delivered though all employee-wide communication

## Slide 6
Stakeholder analysis
High
Low
High
Low
Impact of change
Influence
Stakeholder engagement matrix
Keep satisfied
Involve and engage
Keep informed
Monitor
Source: YYY analysis
 | Low | Medium | High
Whether stakeholder will be impacted by project X | Limited impact | Will be impacted | Significant impact
Influence of stakeholder over project X’s success | Actions do not affect project X | Actions has limited effect on project X | Actions are essential to project X’s success
Keep satisfied
Involve and engage
Keep informed
Monitor
Stakeholder engagement, communication:
  Gain buy-in on key initiatives being rolled-out through conducting 1:1 leadership engagement sessions between YYY’s Senior Management and Head of Service / Function as well during Project Steering Committee/Management Meetings
Stakeholder engagement, communication, training:
  Raise awareness, understanding and buy-in of project at a group and division level through Townhalls, Roadshows, Newsletters, Competitions, Go-Live Success Stories, Go-Live Emails and FAQ documents
  Conduct change readiness assessments to gauge readiness of stakeholders towards the change and assess effectiveness of change management activities
  Train and equip stakeholders on new processes and ways of working as the end users to operationalise new processes
Change interventions
Communication:
  Promote awareness on key changes and benefits of the xxx implementation via Newsletters, Go-Live Emails and Go-Live Success Stories
Communication:
  Promote awareness on relevant changes and benefits of the Transformation as and when required
  Cabinet
  Permanent Secretaries
  Heads of HR
  Project Sponsor
  MDA Local Sponsor
  Vendors/ Suppliers
  Trade Unions
  Change agent network
  Employees
  Line managers
  MDA Executive Team
  Senior Finance team

## Slide 7: Stakeholder analysis
During the change roll-outs, we will conduct a more detailed analysis to identify each stakeholder level of influence and support towards project X These findings will be plotted against the engagement matrix and the required change interventions will be executed. Ultimately, the aim is for all stakeholders to be champions of project X.
Impact of change
Action required: Involve extensively
Involve and consult as much as possible
Involve as change champions to sell the change to others & ‘pull’ others through
Engage to ensure an effective coalition
Action required: Monitor and address cconcerns
Manage proactively
Identify actions & next steps
Sell the benefits
Monitor feedback
Involve in ideas generation, validation workshops, risk planning and issue management
Influence
Action required: Communicate
Keep communicating and selling the benefits
Monitor to ensure they are receiving the correct information
Action required: Inform
Keep stakeholders in the loop and provide regular updates
Ensure they understand the changes that will take place and encourage them to sponsor the initiative, even if they are not directly impacted
Keep satisfied
Involve and engage
Monitor
Keep informed

## Slide 8: Part 2
Stakeholder engagement and communication strategy

## Slide 9
Change management team’s goal for project X
Time
Support for change
Change commitment curve
Informed
Understand
Buy-In
Commit
Negative perception
  Unfamiliar
Shows signs of buy-in for the change
Demonstrates a willingness to ‘Buy-In’ to the change in some fashion and continue the change process
“Try-out” new module / system
The comprehension of the nature and intent of the change as well as where they ‘fit in’
Usually includes an ‘informed pessimism’ stage as they discover that the change will involve some effort
Long-term usage and commitment towards module / system
An examination of the extended implications of the change
When the personal belief is at the point of ‘we are not going back’
Knowledge of the emerging change, but unclear of the scope, impact, or even rationale for the change
The realisation that they will be affected, but not sure how
Confusion
Decision not support implementation
Change aborted after implementation
Over time, through implementing and executing our targeted stakeholder engagement and communication plan, our goal is to bring each employee up the change commitment curve at the right pace.

## Slide 10
Objectives of effective stakeholder engagement and communication
1
2
3
4
5
Potential outcomes
Potential enablers
Objectives
To use existing communication channels within XYZ to communicate key messages regarding project X | Management support, commitment and buy-in Facilitate cascading of information to lower levels | Gains commitment and buy-in Promotes engagement and builds trust
To develop a communication strategy to disseminate the objectives and expectations of project X | Provides a clear future direction for all employees Communication and feedback mechanism to all employees | Creates awareness and understanding of project X to all impacted stakeholders Manages negative sentiments and anxiety as a result of the change
To develop a communication strategy, that addresses the target audience issues and supports the transition to the desired future state | Establish the correct key messaging for each stakeholder group | Stimulates readiness in accepting change and transition Identifies opportunities for all stakeholder to positively and actively engage all employees
To develop and implement a detailed communication plan, including timing, key messages and responsibilities for an individual’s communication actions | Support desired behavior through regular engagements with key stakeholder groups in order to cascade key messages to all employee levels | Facilitates clear and concise two-way communication
To effectively manage and monitor the progress of the communication plan | Communication and feedback mechanism to all employees | Effective communication and stakeholder engagement

## Slide 11
The 5 steps below are critical in establishing an appropriate Stakeholder engagement and communication strategy
Establish the objectives of the stakeholder engagement and communication strategy
Identify and understand the stakeholder’s role to gain insight on how to achieve understanding and buy-in
Identify and leverage the existing communication channels within the organisation as well as confirm appropriate channels channels for engagement
Provide a long-term strategic perspective on stakeholder engagement and communication
Define a set of key messages that are consistent, clear and articulate the reason for and impact of the project
Stakeholder engagement and communication

## Slide 12: Engagement objectives
Consistency and alignment of messages are essential to build trust and advocacy for project X
Provide awareness and understanding about why the project is happening
Reduce the risk of business disruption
Management to promote transparency in building credibility in order to create trust and buy-in
Acknowledge each employee for their contribution thus far and that the project support the change journey
Set and align realistic expectations of what is required of each stakeholder group during the transition to the new systems
Reduce resistance through sharing enough information about the change and creating a sense of inclusion

## Slide 13: Stakeholder engagement and communication channels
Existing stakeholder engagement and communication channels |  |  | 
Channel Type | Channel Name | Content Owner | How can we leverage this channel for project X?
Digital communication | E-Mail | Central communication team | To be the most frequently and widely used communication channel to effectively disseminate formal memos / updates on all project X’s key activities to all employees (i.e. Newsletter, Competitions, Change Readiness Assessment, Go-Live Email, Success Story, etc.) To be used as an instantaneous platform to provide updates that requires immediate call to action (i.e. when employees are required to RSVP to project events: Townhalls, Awareness / Updates / Buy-In Roadshows)
 | Workplace by Facebook | Central communication team | This channel will be used to instantaneously address any concerns or questions related to project AAA which will facilitate two-way communication with all employees and thus: Increase employee engagement Enhance relationship building Build a transparent culture Share project X contact details (i.e. xxx.com) to provide employees the opportunity to privately express their concerns, feedback or suggestions
 | Intranet | Central communication team | To be used as a centralised Knowledge Management repository to ensure all employees will focus on all project X’s key initiatives All relevant documentation (i.e. AAA guidelines, blueprint, policies) can be uploaded onto the Intranet / Portal/etc. which provides all employees the ability to easily perform full-text search for these readily available documents This is an effective channel for users from each division to easily create and update their necessary information / documents quickly and efficiently

## Slide 14: Stakeholder engagement and communication channels
Existing Stakeholder engagement and communication channels |  |  | 
Channel Type | Channel Name | Content Owner | How can we leverage this channel for project AAA?
Digital communication | Roadshows | YYY Change Management Team | To raise awareness, understanding and buy-in Use this channel to have effective direct engagements with the masses to: Share timeline, project progress, key achievements, benefits, milestones (i.e. Go-Live dates) Address any questions / concerns and obtain feedback / suggestions Provide reassurance that there will be minimal disruptions to their day-to-day operations Emphasize that the involvement of all employees is critical to make project X a success
 | Engagement Sessions | YYY Change Management Team | To be used as a platform for X’s Change Management Team / Senior Management to engage Senior Management/Change Agent Network on a 1:1 basis Understand and manage their expectations / pain points Address any of their questions / concerns and obtain their feedback / suggestions Acknowledge that their leadership and involvement is critical throughout project X Share impactful talking points for them to use when communicating to the rest of their employees about project X Effective communication channel to conduct an informal pulse check to monitor the overall effectiveness / performance of project X thus far
Events | Townhalls | YYY Change Management Team | Use this communication channel to effectively engage the masses about project X to enhance their awareness and buy-in To be used as a platform to share overall project progress, key achievements and upcoming milestones of project X Provides the opportunity to address questions / concerns and obtain feedback / suggestions publicly which builds a transparent culture and increases relationship building with all employees

## Slide 15
Why change?
Change impact and consequences
Issues and challenges
Required involvement
Project updates
The reason for the project and the case for change
Ongoing and tailored updates to all levels of stakeholders
How the changes impact on stakeholders
Address the issues and challenges that stakeholders will face
Why and how stakeholders can be involved
Key message - themes

## Slide 16
Key messages for identified stakeholder groups
Stakeholder Groups
Key Messages
Examples
Senior Management
(incl. project Steering Committee)
Keep updated and informed
Change Sponsor
Actively involve and engage where necessary
Business Champions
Actively involve and engage where necessary
Change
Agents
Actively involve and engage where necessary
Key Users
Agents
Actively involve and engage where necessary
Awareness of the implementation, high-level timeline, key milestones, project progress, roles and responsibilities
All Employees
Actively involve and engage where necessary
Business Process Owners
Actively involve and engage where necessary
Awareness of the Implementation, high-level timelines, key milestones, project progress
Project timeline, stakeholder engagement and communication plan, change impact assessment, roles and responsibilities, tasks to perform, inputs required to push initiatives forward
Awareness of the Implementation, high-level timeline, key milestones, project progress, resourcing needs, inputs required
Division Blueprint sign-off
Project timeline, stakeholder engagement and communication plan, roles and responsibilities, expectation, tasks to perform, inputs required, post implementation activities
Project timeline, stakeholder engagement and communication plan, change impact assessment, roles and responsibilities, tasks to perform, inputs required
Provide strong input into design of “blueprint”
Documentations and advice required on system configuration and integrations
Business user coordination for UAT testing and sign-offs

## Slide 17: Criteria for stakeholder engagement and communication strategy and plan
Capabilities to reach a wider audience
Project X will impact all staff at all levels to a certain degree but the impact varies per stakeholder group
There will be common messages needed to be shared by all the stakeholders including the objectives and impact of the project and tailored messages at division level
The communication channels must be capable in reaching a wider audience and the public, if required
Communication channels must be able to disseminate messages on a timely basis
This will ensure that decisions and actions to be made by the stakeholders are made within the required timeframe
Capabilities to disseminate messages in a timely manner
1
The nature of the messages to be communicated
Communication messages can be used for various reasons including to educate, to facilitate buy-in and to seek decision from the various stakeholders
The channels to be utilised in Projext X must be able to facilitate the communication of the various messages
2
Capabilities to meet the communication needs of the targeted stakeholders
The communication channels must be able to take into account the different needs of the various stakeholders including their level of influence and impact on the project and their hierarchy in the organisation
3
Cost-effectiveness of using the channels
The communication channels must also be cost-effective in order to avoid wastage
Cost-effectiveness will include the cost of establishing the channels, cost of accessibility to the channels and the cost of maintaining the channels
4
5

## Slide 18: Part 3
Detailed stakeholder engagement and communication plan

## Slide 19: Example: Communication calendar
Channels of Stakeholder Engagements and communication
  Face-to-Face
  Digital communication
  Events
Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
“Awareness Phase”
Townhall #1
Townhall #2
Townhall #3
Townhall #4
FAQ Document #1
FAQ Document #3
FAQ Document #4
Go-Live Email from Senior Management #1
Go-Live Email from Senior Management #3
Go-Live Email from Senior Management #4
Go-Live Success Story
Go-Live Success Story
Go-Live Success Story
Competition -“Awareness” Phase
Project Steering Committee Meeting (Monthly or upon request, when key decisions are required - ad-hoc)
Working Committee Meeting (Bi-Weekly or upon request, when key decisions are required - ad-hoc)
Project Committee Meeting - PMO, project Delivery & Advisory (Weekly or upon request, when key decisions are required - ad-hoc)
AAA Newsletter
Change Readiness Assessment #1
Change Readiness Assessment #2
Change Readiness Assessment #3
“Understand Phase” Roadshow
“Buy-In Phase” Roadshow
“Did You Know?” Intranet Banner #1
“Did You Know?” Intranet Banner #2
“Did You Know?” Intranet Banner #3
Competition -“Understand” Phase
Competition -“Buy In” Phase
Go-Live Email from Senior Management #2
FAQ Document #2
Change Readiness Assessment #4
2021
2020
2022
Conducted by XYZ, supported by CM Team
Conducted by YYY CM Team

## Slide 20: High-level plan
communication
Stakeholder Engagements
Explore
Run
Email reminder
to Key Users
(End User Training)
Email to share preparations and expectations for End User training
Trial Data
Migration
User Acceptance Testing (UAT)
Survey (Value Add)
Pulse survey via email to measure employee sentiments to compare against baseline
Blueprint Sign Off
Email reminder
for HOD
Reminder of Division Blueprint Sign-Off
Go-
Live
Realise
Deploy
Email reminder to
Key Users
Email to share preparations and expectations for UAT
Day 1 Go-Live
Welcome email on organisations system implementation and reminder to organise administration matters
Email to involve Key Users
Email to share timing and expectations regarding Trial Migration and UAT, as well as request for their availability
Management Committee Meeting (Monthly or upon request, when key decisions are required - ad-hoc)
Informal Breakfast Session for Change Sponsor with his/her change agent network within the division (Monthly)
Informal Breakfast Session by project X with selected employees of the division (Every 3 Months)
Change Impact Assessment
Key User
Training
End User
Training
Email reminder to Key
Users (Train the Trainer)
Email to share preparations and expectations for Train the Trainer training
1:1 Leadership Engagement Session between Senior Management and HOD (Twice)
Email reminder to
Key Users
Email to share preparations and expectations for Trial Data Migration
Group Blueprint
Sign Off
Cutover Checklist
Comprehensive checklist via email of administrative matters and things-to-do before Go-Live
Email Countdown
till Day 1 Go-Live
Countdown email to generate excitement, raise awareness and ensure employees are prepared for “x” number of days till Day 1 Go-Live
The following anchor activities are planned to reach out to all impacted stakeholder groups within each division / module roll-out

## Slide 21: Part 4
Key messages for stakeholder engagement execution

## Slide 22
Stakeholder engagement execution – December 2021
Stakeholder engagements | Engagement name | Stakeholders | How | Key messages | Date | Location | Action items | Accountability
 | Project Steering Committee Meeting | Steering Committee Members | Face to face | Share updates on overall project timeline and key milestones Discuss direction of the overall project Make decisions on unresolved issues and risks encountered by the Working Committee | Monthly from December 2020 – April 2022 |  | Confirm date and time Prepare, update deck and action items Send invitation Logistics arrangements (if required) | YYY PMO Team
 | Working Committee Meeting | XYZ Deputy CEO & Deputy MD, Business Champions, Appointed Representatives | Face to face | Share updates on overall project timeline and key activities Discuss issues especially technical issues, risks and mitigation plans raised by the project team Address concerns and provide reassurance | BI-Weekly from December 2020 – April 2022 |  | Confirm date and time Prepare, update deck and action items Send meeting invite Logistic arrangements (if required) | YYY PMO Team
 | Project Committee Meeting | XYZ CIO & Project Director, XYZ PMO, ZZZ PMO | Face to face | Share updates on overall project progress and key activities Share recommendations of deliverables Discuss project dependencies, issues and risks if any and mitigation plans | Weekly from December 2020 – April 2022 |  | Confirm date and time Prepare update deck and action items Send meeting invite Logistic arrangements (if required) | YYY PMO Team

## Slide 23
Stakeholder engagement execution – January 2022
Stakeholder engagements | Engagement name | Stakeholders | How | Key messages | Date | Location | Action items | Accountability
 | Project Steering Committee Meeting | Steering Committee Members | Face to face | Share updates on overall project timeline and key milestones Discuss direction of the overall project Make decisions on unresolved issues and risks encountered by the Working Committee | Monthly from December 2020 – April 2022 |  | Confirm date and time Prepare, update deck and action items Send invitation Logistics arrangements (if required) | YYY PMO Team
 | Working Committee Meeting | XYZ Deputy CEO & Deputy MD, Business Champions, Appointed Representatives | Face to face | Share updates on overall project timeline and key activities Discuss issues especially technical issues, risks and mitigation plans raised by the project team Address concerns and provide reassurance | BI-Weekly from December 2020 – April 2022 |  | Confirm date and time Prepare, update deck and action items Send meeting invite Logistic arrangements (if required) | YYY PMO Team
 | Project Committee Meeting | XYZ CIO & Project Director, XYZ PMO, ZZZ PMO | Face to face | Share updates on overall project progress and key activities Share recommendations of deliverables Discuss project dependencies, issues and risks if any and mitigation plans | Weekly from December 2020 – April 2022 |  | Confirm date and time Prepare update deck and action items Send meeting invite Logistic arrangements (if required) | YYY PMO Team

## Slide 24
Stakeholder engagement execution – February 2022
Stakeholder engagements | Engagement name | Stakeholders | How | Key messages | Date | Location | Action items | Accountability
 | Project Steering Committee Meeting | Steering Committee Members | Face to face | Discuss/Share updates on overall project timeline and key milestones Direction of the overall project Make decisions on unresolved issues and risks encountered by the Working Committee | Monthly from December 2020 – April 2022 |  | Confirm date and time Prepare, update deck & action items Send invitation | PMO Team
 | Working Committee Meeting | Leadership A & Leadership B, Organisational Champions, Appointed Representatives | Face to face | Share updates on overall project timeline and key activities Discuss issues especially technical issues, risks and mitigation plans raised by the project team Address concerns and provide reassurance | BI-Weekly from December 2020 – April 2022 |  | Confirm date and time Prepare, update deck and action items Send meeting invite Logistic arrangements (if required) | PMO Team
 | Project Committee Meeting | IT & Project Director, PMO | Face to face | Share updates on overall project progress and key activities Share recommendations of deliverables Discuss project dependencies, issues and risks if any and mitigation plans | Weekly from December 2020 – April 2022 |  | Confirm date and time Prepare, update deck and action items Send meeting invite | PMO Team
 | Townhall #1 | All Employees | Face to face | Share overall progress and updates of the project including the timeline, ongoing and upcoming milestones Share benefits and values of project AAA which were derived from key achievements Address questions, concerns, feedback and provide reassurance | February 2021 |  | Prepare relevant slides and key talking points | Supported by CMO / PMO Team

## Slide 25: Part 5
Example of monthly calendar plan of stakeholder engagements and communication

## Slide 26
Stakeholder engagement and communication calendar : Legend
Legend:
Meeting
Newsletter
Townhall
Intranet banner
Change readiness assessment
Roadshow
FAQ document
Email
Success story
Competition

## Slide 27
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
 |  |  |  | 1 | 2 | 3
4 | 5 | 6 | 7 | 8 | 9 | 10
11 | 12 | 13 | 14 | 15 | 16 | 17
18 | 19 | 20 | 21 | 22 | 23 | 24
25 | 26 | 27 | 28 |  |  | 
Example: January 20XX – organisation wide stakeholder engagement and communication calendar*
*For each division/module, personalised stakeholder engagement and communication calendars will be developed upon its roll-out.
AAA Newsletter #3
Project Committee Meeting
Project Committee Meeting
Project Committee Meeting
Project Committee Meeting
Working Committee Meeting
Working Committee Meeting
Project Steering Committee Meeting
New Year’s Day
Working Committee Meeting
Townhall #1
“Did You Know?” Intranet banner #1
Change readiness assessment #1
Legend:
Meeting
Newsletter
Townhall
Intranet banner
Change readiness assessment

## Slide 28
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
 |  | 1 | 2 | 3 | 4 | 5
6 | 7 | 8 | 9 | 10 | 11 | 12
13 | 14 | 15 | 16 | 17 | 18 | 19
20 | 21 | 22 | 23 | 24 | 25 | 26
27 | 28 | 29 | 30 | 31 |  | 
Example: May 20XX - stakeholder engagement and communication calendar*
*For each division/module, personalised stakeholder engagement and communication calendars will be developed upon its roll-out.
AAA Newsletter #6
Legend:
Meeting
Newsletter
Project Committee Meeting
Project Steering Committee Meeting
“Awareness” Phase Roadshow
“Awareness” Phase Roadshow
“Awareness” Phase Roadshow
“Awareness” Phase Roadshow
Roadshow
Working Committee Meeting
Project Committee Meeting
Project Committee Meeting
Project Committee Meeting
Working Committee Meeting
Project Committee Meeting
“Awareness” Phase Roadshow
FAQ document #1
Go-Live Email from Senior Management #1
FAQ document
Email

## Slide 29: CONTACT US
TIU_Jamaica
TIU_Jamaica
TIUJamaica
www.publicsectortransformation.gov.jm
letusknow@transformation.gov.jm
Transformation Implementation Unit
Public Sector Transformation