## Slide 1
[Project name] Change Impact Analysis Report and Action Plan Template

## Slide 2
Overview and purpose
CONFIDENTIAL
Description | This document provides a template to report on and present a summary of findings from the high-level Change Impact Analysis (CIA). |  | 
How to use this template | The template should be updated with insights gained from completing the CIA with project teams and key stakeholders, supported by the data captured. Once completed, the high-level CIA report should be shared with members of the Business Change team, key business stakeholders and broader project team. This will help inform the change management planning. |  | 
When to use this template | This table should initially be used when conducting high-level Change impact analysis and subsequently when conducting detailed Change Impact Analysis |  | 
Owner |  | Intended audience | Project team Programme leadership Key impacted stakeholder groups
[Program Name] Version: Created By:

## Slide 3
Document control
CONFIDENTIAL
[Program Name] Version: Created By:
Document title | Change impact analysis report and action plan template |  | 
Document version | Version 1.0 |  | 
Last updated | 20 January 2022 |  | 
Updated by | xxx | Document location | xxx
Document history |  |  |  | 
Author | Date Modified | Version | Brief Description of Changes | Reviewed By
x | 20 January 2022 | 1.0 | XXX | XXX

## Slide 4
Contents
CONFIDENTIAL
[Program Name] Version: Created By:
# | Section | Page
1 | Structure of the report | 5
2 | Executive summary | 7
3 | Findings | 10
4 | Appendix | 12

## Slide 5: Structure of the report

## Slide 6
Structure of the report
CONFIDENTIAL
[Program Name] Version: Created By:
    This tool highlights the impact of change on the organisation by contrasting employees’ ‘current’ and ‘to-be’ states in relation to behaviour, job process and role, job location and technology use.
    Once you have conducted the change impact assessment, you need to take the insight you have learnt and turn them in to tangible actions that will enable you to reduce the expected change impact of a role or function. It is important to write a report with your key findings against the assessed impact areas and an action plan of the activities you will conduct to minimise the change impact.
    Structure of the change impacts analysis report and action plan:
Executive summary
Summary heat map findings
Findings:
  Heat map
  Change Impacts by business units/department
Appendix

## Slide 7: Executive summary

## Slide 8
Executive summary
CONFIDENTIAL
[Program Name] Version: Created By:
    This section of the report should:
    Provide a brief background of the programme, its objectives, timescales and key impacted stakeholders
    Give an overview of the approach taken in conducting the change impact analysis
    Summarise the change impacts of the solution/system implementation
    Summarise key change messages that should be described and then interpreted in terms of the impact at a team level

## Slide 9
Executive summary – key findings
[Program Name] Version: Created By:
B. Key process information
C. Key process roles impacted
D. Key changes
G. Leadership for change sponsors |  |  | 
 | To be updated | To be updated | To be updated
 | To be updated | To be updated | To be updated
 | To be updated | To be updated | To be updated
 | To be updated | To be updated | To be updated
 | To be updated | To be updated | To be updated
 | To be updated | To be updated | To be updated
 | To be updated | To be updated | To be updated
 | To be updated | To be updated | To be updated
A. Current state assessment summary
E. User groups impacted | Numbers of users | 
 | CLIENT SERVING PROFESSIONAL | RESOURCE ADMIN
F. Key requirements from change perspective (Comms, training, and change agent network)
H. Key process challenges and risks
.

## Slide 10
Executive summary – key findings
CONFIDENTIAL
[Program Name] Version: Created By:
Team | Impact | Key changes messages | Leading to…/requirement for…
Dispatch |  | Move away from manual system to automated system, with increased automation enabling over 90% of jobs being auto-dispatched Capability to continually enhance business rules to optimise scheduling algorithm | Dispatchers role to change from a dispatch expert to one who manages by exception. Requirement to trust the auto-scheduler to effectively dispatch – manual dispatch by exception only System skills and experience based hierarchies removed
Resource management |  | Single view of all workload and asset data across the organisation (replacing multiple spreadsheets) and visibility of asset hierarchy to the field All work orders linked to assets | More robust planning and modeling, reduced dependency on excel sheets and ability to identify resource/workload constraints more clearly Ability to focus on more strategic planning away from data manipulation
Engineering services |  | Consolidation of multiple systems in one single asset repository for single source of M.I reporting Capability to support additional areas of the business with MI reporting | Requirement to trust new system as the sole data source, as there is no longer the ability to verify data in multiple systems Greater emphasis on accurate asset data Potential rebuild of approx 300 MI reports to enable continued provision of M.I
Commercial |  | Single view of all workload / asset data across business through supported by single BI reporting tool, will replace multiple sources of M.I from legacy systems. | Provision of single consistent set of M.I with direct reporting access
Customer experience |  | Greater information available to call agents e.g. contact details, status updates, all work orders now visible. | Improved first call resolution, promoting cultural change towards ownership of enquiries Parallel processes necessary for viewing job data, until new call handling interface (CRM) in place Potential for increased call handling time associated with handoff
SAMPLE

## Slide 11: Findings

## Slide 12
Ministries, Departments and Agencies (MDAs) | # FTE | # of Impacted FTE | % of Impacted FTE | Current state | Future state | Type of impact |  |  | Change consideration
 |  |  |  |  |  | People | Process | Tech | 
MDA A | 270 | 270 | 100% | MDA A currently promotes phone numbers as the primary contact method via in mail campaigns, social media and websites. | In the future, we will divert customer enquiries from the contact centre to online channels |  |  |  | 
MDA B | 270 | 270 | 100% | There is currently no active management online and social media channels for answering enquiries which is ultimately impacting service levels | Customer enquiries will not be telephone based, and there will be active management of all online and social media enquiries |  |  |  | 
Major impact
Moderate impact
Minor impact
Key:
FTE – Full time employees
Summary heat map findings
    Overview of the change impacts in the form of a heat map:
    The overall impact of the new solution/system on the Business should be detailed at a organisational unit and team level within a Heat Map, as illustrated below. The RAG (Red, Amber, Green) status for the Heat Map is derived from both the percentage of the team impacted and the complexity of the change according to the key:
ILLUSTRATIVE EXAMPLE

## Slide 13
Summary of findings by process
These processes must be known in order to complete the high level CIA |  |  | Complete first iteration for high level CIA; review and update with more information for detailed CIA |  |  |  |  | 
Ref | L1 Process | L2 Process | Current state | Future state | Description of the change impact | Division | Org area(s) | Team
 | Record the L1 process step as per the process documentation | Record the L2 process step as per the process documentation | Record how the process is performed now | Record the changes for the process e.g. what is changing and how will it be different from what they do today? | Describe the impact of the change e.g. the new system will no longer allow manual corrections so the team will need training on the new process | Record the function impacted; note you should also include any external stakeholder impacts, e.g. to customers (both B2B and B2C) or governing bodies | Record the business area(s)impacted | Record the relevant team impacted
1 | Customer to call phone number for enquiry | Customer to click through the various options and select the appropriate customer service representative they wish to talk to. | MDA currently promotes phone numbers as the primary contact method via in mail campaigns, social media and websites | In the future, we will divert customer enquiries from the contact centre to online channels | The processes for customers to make an enquiry The skills of the contact centre to respond to online enquiries rather than phone based. | Customer | Customer support | 1
ILLUSTRATIVE EXAMPLE

## Slide 14
People | 
There will be a reduction in FTE by consolidating sites, roster optimisation, digital strategy and some volume/average handling time (AHT) reduction. These changes will have a direct impact on the contact centre staff through operational excellence and reduction in resources required for the future structure as well as an optimised roster. | 
Process | 
Due to the changes in enquiry channels for customers and the technology solutions for staff the contact centre staff will need to be upskilled and retrained. There will be a requirement for processes to be remapped and training developed and deployed across the new site structures. | 
Technology | 
The digital strategy will enable website improvements, new interactive voice recording (IVR) routes and messages as well as increased coverage of outages in IVR messages. The change will impact all contact centre staff, specifically the consultants directly answering customer queries. The new solution will mean enquiries will be directed to online channels which call centre staff will also need to be trained to manage. | 
Total FTE | 370
Total number of impacted FTE | 370
Overall scale of change | 
Summary department findings
ILLUSTRATIVE EXAMPLE

## Slide 15: Appendix

## Slide 16
CONFIDENTIAL
[Program Name] Version: Created By:
Appendix: Magnitude of the change impact
Evaluating the magnitude of the impact based on the complexity of change consistently across MDAs is critical to planning the appropriate risk mitigations to enable a successful implementation of new policies, processes and organisational structures, and technology.
Magnitude of change |  |  |  | 
Impact level | Degree criteria | People/behaviour | Process | Technology
Low | Most impacts will fall into this category where there is a minimal change and it is categorised as a low impact. Users may need training in order to learn new processes and systems. | Minimal changes that impact skills, capabilities, culture, behaviours, structures, interactions with other areas of business. | Few changes to existing processes/policies. | Low to moderate changes occur in systems or applications already being used.
Medium | Many ways in which how employees do their job will change. (e.g., in addition to process and system training, new skills may be require; work may shift to a new department) | Moderate amount of changes or additions to skills, capabilities, culture, behaviours, structures, interactions with other areas of business. | Moderate changes to existing processes/policies and/or new processes of low to moderate complexity. | High complexity of changes in current system. Low to moderate complexity of changes requiring use of new systems, applications, or tools.
High | There is a fundamental change in the way individuals do their job; they will require significant preparation to perform their job in the future. Any organisational structure changes. | High amount of changes or additions to skills, capabilities, culture, behaviours, structures, interactions with other areas of business. | High amount of changes to existing processes/policies and/or new processes of high complexity. | Moderate to high complexity changes requiring use of new systems, applications, or tools.

## Slide 17: CONTACT US
TIU_Jamaica
TIU_Jamaica
TIUJamaica
www.publicsectortransformation.gov.jm
letusknow@transformation.gov.jm
Transformation Implementation Unit
Public Sector Transformation