## Slide 1
Change Management Strategy Example

## Slide 2
Document control
CONFIDENTIAL
[Program Name] Version: Created By:
Document title | Change Management Strategy |  | 
Document version | Version 1.0 |  | 
Last updated | 21 January 2022 |  | 
Updated by | xxx | Document location | xxx
Document history |  |  |  | 
Author | Date modified | Version | Brief description of changes | Reviewed by
x | 21 January 2022 | 1.0 | XXX | XXX

## Slide 3
Contents
CONFIDENTIAL
[Program Name] Version: Created By:
# | Section | Page
1 | Introduction | 4
2 | Context of the change | 7
3 | Content of the change | 10
4 | Complexity of the change | 14
5 | Course of action | 17
6 | Appendix | 49

## Slide 4: Introduction

## Slide 5
Introduction
CONFIDENTIAL
[Program Name] Version: Created By:
“A structured approach for transitioning individuals, teams, and organisations from a current state to a desired future state”
A process to align expectations across (ENTITY A) and build stakeholder buy-in
1
A process to ensure that the organisation is ready, willing, and able to function in the new environment
2
3
A process to help ensure the transition process to the target state is smooth and benefits are realised
What is a change management programme?

## Slide 6
Introduction
What is a change strategy?
CONFIDENTIAL
[Program Name] Version: Created By:
The change strategy is a macro-level view of the main objectives of the change management effort. It highlights the key reasons for the change and the key change activities.
It sets the stage for all the change work that follows and it begins to develop an understanding of the course of action based on the following:
Context of the change – the circumstances from which the change is initiated
Why do we need to change?
Builds a sense of urgency and vision.
Content of the change – the change itself
What is changing? When? Who is impacted?
Strategy, people, process, organisation design, communication, training, leadership, and cultural perspectives.
Complexity of the change – the magnitude and nature of the change
How big and how challenging will it be to change?
Cultural, emotional, and political environment in which the change will occur.

## Slide 7: Context of the change

## Slide 8
Understanding how X programme fits within Entity X transformation journey
CONFIDENTIAL
[Program Name] Version: Created By:
Context of the change
Implementation of the XX platform is a huge undertaking requiring the support and commitment of (ENTITY A) employees and leadership, however it is important to remember that this is the first step in a long journey.
The XXX implementation goal for 2021 is to deploy a skeleton system that delivers absolute minimum functionality needed to perform the job, not the functionality needed to perform the job with all the bells and whistles, which will come in future phases.
The current XXX implementation is simplifying what we have now to build capabilities in the future.
PROVIDE DETAILS ON WHY WE NEED

## Slide 9
State the transformation vision here
CONFIDENTIAL
[Program Name] Version: Created By:
Yesterday
Today
Tomorrow
  In the past 25 years, ENTITY A has led the industry as a data storage company. However, in the past 4 years, the industry’s landscape has radically changed and so has its vision.
  To drive maximum customer value and support in an ever-evolving digital landscape, including the transition to cloud technologies, ENTITY A is focusing on becoming a top player in the data management industry.
  ENTITY A will concentrate on its strategic solutions business including all-flash storage, operating system and management technology to meet market demands. Internal functions, processes and technologies will evolve to improve ways of working and reduce complexities that have become engrained overtime.
How?
Why?
What?
  Acquisitions
  Expanded service and product offerings.
  Current market and customer trends
  Geographical changes, technology improvements and adoption
  Economic performance within the country.
  Review and simplify sales process
  Develop structured approach to selling
  Reducing ambiguity
  Save money and plan for the future.
ILLUSTRATIVE EXAMPLE

## Slide 10: Content of the change

## Slide 11
Recognising current state pain points
Areas of opportunity as we continue to implement an improved xxx
CONFIDENTIAL
[Program Name] Version: Created By:
No tool to personalise and differentiate ENTITY A for accounts
No clear process to invite customer contacts to extended marketing campaigns
No clear visibility into xxx
Excessive fields to populate
No single location to complete job activities
Manual process to load contacts into system
No full visibility across xxx
No access on a mobile device
The integrity of the data is low – xxx

## Slide 12
What is changing for the team…
This journey requires everyone involved to understand the need to change and the future vision
CONFIDENTIAL
[Program Name] Version: Created By:
Simplified process
A system providing flexibility to respond to the customer
Reduced ambiguity through a clear, structured approach and processes
Ability to connect digitally
Improved data integrity
Highly complex, customised processes
The system was designed with a single output in mind
Too many ways to complete tasks from ambiguous and customised processes
Lack of mobile / on-the-go capabilities
Expensive
Challenges in delivering outputs due to the delay of inputting data
Low data quality from unstructured and confusing input processes.
Case for change
Future vision

## Slide 13
… and the key mindset and behaviours required to successfully implement
CONFIDENTIAL
[Program Name] Version: Created By:
  Out-of-the-box use will be prioritised to ensure ENTITY A can benefit from future capability enhancements
  Unless legal, regulatory, or specific value-add requirements exist, ask whether customisation or complexity is needed
  Adopt a “shortest path” mentality. If a process has too many steps that doesn’t add value, it’s making the user journey too long
  Local optimisation will need to align with XX needs
  Fewer processes and mobile/tablet access will enable our people to get off the keyboards and be in front of the customer.
Prioritise simplification and challenge complexity
  Optimising systems and reducing the time to complete within the process can release investment for other things
  Identify future, up and down-stream improvement and opportunities bringing ENTITY A’s vision to life.
Be strategically forward-looking
  Moving to a simpler environment will eliminate some manual processes and provide mobile capabilities. Individuals will be able to action some tasks immediately during the Optimizing process
  Scale and complexity of opportunities will determine if mobility is reasonable. ENTITY A staff and partners must manage expectations of users.
Integration, flexibility and mobility
  A structured way of doing what we need, when we need may be different but drives future value
  Data flows in an integrated way through the system – we can’t just go back and “fix it”. Need to enter data properly, the first time
  Upfront validation and accuracy will be critical to improving XXX and data integrity.
Smarter, focused process and improved data quality

## Slide 14: Complexity of the change

## Slide 15
Understanding the complexity of the change
CONFIDENTIAL
[Program Name] Version: Created By:
Change adoption
Time
Change announced
Change commitment dip
Increased stakeholder buy-in
Go-live
Sustained adoption
Complexity of the change
The scope and impact of the Transformation is far reaching and will touch every part of the customer service team and ENTITY A partners and will have ripple effects across the enterprise
We will develop and refine our understanding of how different stakeholder groups will be impacted and the degree of engagement they will require based on the type of change
Given the national nature of the programme, there will be additional complexities and considerations required to ensure regional and partner differences are managed properly in terms of training requirements and knowledge transfer.

## Slide 16: Course of action

## Slide 17
Critical success measures and outcomes
CONFIDENTIAL
[Program Name] Version: Created By:
We have determined critical success measures and outcomes by level in the organisation.
GoJ
Organisation A
End User (Individual/Partner)
  XXX
  xxx
  xxx
Outcomes
Outcomes
Outcomes
  xxx
  xxx
  xxx

## Slide 18
Challenges with managing change
CONFIDENTIAL
[Program Name] Version: Created By:
We have taken into consideration the unique aspects of ENTITY A’s business and culture, and recognised challenges with managing change.
Technology
XXX
Organisation
XXX
Process
XXX
Leadership
XXX
People & Skills
XXX

## Slide 19
The change programme is rooted in a change management framework
CONFIDENTIAL
[Program Name] Version: Created By:
Change Strategy & Leadership Engagement
Business readiness
Change impacts: Development of a comprehensive picture of major stakeholder impacts & areas of resistance
Knowledge transfer: Establishment of a regular cadence to share information with key stakeholders as part of a transition plan
Training and support: Enablement of individuals affected by the change through training and support so that they become capable in the new ways of working and any new skills required
Measurement
Change measurement: Development and adherence to KPIs that track whether users are ready, willing and able to adopt change
Change strategy and leadership engagement
Change strategy: Establishment of the strategies and plans to facilitate the transition to the future state and mitigate deployment risks; continuous refinement and improvement of plans and activities based on learnings and insights from measurement activities
Leadership engagement: Alignment of leadership to the Transformation vision and behaviors required to actively lead and sponsor the change; supported by a structured cadence of engagement, enabling two-way communication, input and alignment of future state cultural values, mindsets and critical behaviors to the new ways of working
Business engagement
Communications: Engagement and effective communication to impacted stakeholders – from xxx
Stakeholder engagement and analysis:
Identification of the required business engagement and business readiness needs to support stakeholder engagement efforts based on the number and types of impacts and stakeholder groups
Change network: Creation of a group of employees at various levels who provide advice, activities, two-way communication and support to increase likelihood of engagement across ENTITY A

## Slide 20
 | 2019 |  | 2020 |  | 2021 |  | 2022 |  |  | 2023
Project Stage |  |  |  |  |  |  |  |  |  | 
Sponsorship and Stakeholder Engagement & Communication |  |  |  |  |  |  |  |  |  | 
Impact Assessment and Change Readiness |  |  |  |  |  |  |  |  |  | 
Learning and Development |  |  |  |  |  |  |  |  |  | 
GOJ Alignment |  |  |  |  |  |  |  |  |  | 
Benefits Realisation and Measurement |  |  |  |  |  |  |  |  |  | 
Business Readiness |  |  |  |  |  |  |  |  |  | 
Sustainability / Reinforcement |  |  |  |  |  |  |  |  |  | 
Focal Areas
Go / No go decision
Other 3rd Party ENTITY A detailed briefings
Sponsor meetings
Key Sponsor stakeholder engagement activities
Detailed Staff awareness campaign and briefings
Agree Sponsors roles and responsibilities
Staff sensitisation workshop
Identify key partners or ENTITY A Sponsors
Change Impact Analysis
Change Assessment 1
Change readiness activities
CAN Mobilised
Training Logistics
Training Deployment
Training Evaluation / Archiving
Coaching Plan
Coaching activities
Resistance management activities
Resistance Management Analysis
Business Readiness Checklist design
Benefits planning
Benefits Review and tracking
Measurement Tracking and Reporting
Business Readiness Validation
xxxx
xxxx
xxxx
xxxx
xxxx
Plan
Reinforcement activities
KT Activities Complete
Through integrated activities focused on transformational change
ILLUSTRATIVE EXAMPLE

## Slide 21
Strategies and plans to facilitate transition to the future state
CONFIDENTIAL
[Program Name] Version: Created By:
We will leverage the following:
Change strategy: Provides the overall framework for all change activities and is created based on an understanding of context, content and complexity of the change
Change plan: Articulates which types of change activities are best suited to help prepare and motivate stakeholders to engage in and sustain the change effort based on the impact assessment findings
Leadership engagement: Defines how we will engage leadership to champion the change, maintaining a focus on the business case and value to be delivered by bringing the organisation along with them.
Actions:
Align leadership on the vision and case for change, clearly articulating the future state
Engage senior leaders to be the face of the project and “live the change” ensuring support for the project and impacted stakeholders is visible across the organisation
Agreement on value and change activities with the overall transformation and other strategic initiatives to ensure messages are aligned and impacts to stakeholder groups are understood and managed.

## Slide 22
Developing the change plan
CONFIDENTIAL
[Program Name] Version: Created By:
The change plan defines the solution to ensure adoption and benefits realisation; it outlines the change management activities selected for the project as needed to move impacted stakeholders along the change commitment curve
The change plan:
Provides answers to the questions of “how we will bring about the change?” and “how will we know we are progressing successfully?”
Aligns and tailors specific interventions for the change impacts to be addressed across the impacted stakeholder groups
Defines the mix, sequence, pace, and measures associated with the change activities
Becomes the roadmap for the change journey, which will be refined and tailored for each deployment.

## Slide 23
Engaging executive leadership thoughtfully
CONFIDENTIAL
[Program Name] Version: Created By:
Support for Change
Stakeholders are aware that a change process is under way
Stakeholders understand the reason, benefit, extent and impact of the change.
Stakeholders accept the change, consider it positive and agree to implications.
Stakeholders are committed, actively supporting and living the change.
Commitment
Acceptance
Understanding
Awareness
Inform:
Change outcomes
Clarify:
Driving change
Convince:
Supporting change
Involve:
Change commitment
1
2
3
4
1
2
3
4
Emphasising sustained, visible sponsorship
Setting and communicating direction
Leading/supporting the change
Mitigating issues and barriers.
Building acceptance and personal responsibility
Specifying what needs to be delivered
Driving benefits of change.
Coordination of change to help ensure realisation of the benefits
Depth of Impact knowledge
Project benefits and KPI measurements
Necessities for change.
Provide stakeholders with knowledge, skills, and processes for success
Process training
Support of training metrics
Identifying gaps and areas of value.
Actions

## Slide 24
By informing leaders of key actions and behaviours that drive change
CONFIDENTIAL
[Program Name] Version: Created By:
  Develop a clear vision for what you are trying to achieve
  Create a sense of urgency to convince others
  Communicate opportunities for your organisation that can only be realised through change
  Use data that supports the claim that change is necessary.
Inform
Maintain momentum and anchor the change in the organisations culture
Promote regular recognition of important achievements associated with the change
Celebrate wins by rewarding the team.
Encourage story-telling
Acknowledge the effort of the team’s persistence toward the vision.
Remind them of their journey and progress achieved.
  Produce highly visible quick wins to foster participation
  Empower others to feel free to act on the vision
  Increase opportunities for employees to openly discuss ideas about the Change
  Acknowledge that change is an uncomfortable space and teams should respect the different pace that individuals will need
  Be firm that resistance or intentional roadblocks are not tolerated.
Convince
Involve
  Define the change in terms of process, technology, policy, and behaviors
  Keep communications simple and track their effectiveness
  Use existing meetings and communications to address questions and communicate status
  Be visible and easily accessible for informal conversations
  Demonstrate behaviors now, and hold your leadership team accountable for doing the same.
Clarify
To help enable sponsorship and leadership alignment to drive change and build awareness

## Slide 25
Engagement and effective communication to impacted stakeholders
CONFIDENTIAL
[Program Name] Version: Created By:
We will leverage the following:
Stakeholder analysis: A systematic approach to identify and prioritise groups and individuals impacted by the Transformation programme
Communications and engagement strategy: A framework that provides guidance for effective interventions and communication techniques to bring targeted stakeholders and stakeholder groups along the commitment curve
Communications plan: A plan that translates the roadmap into defined activities through the duration of the program. Themes drive the messaging of the communications.
Actions:
Align all programme stakeholder management and communications activities with the overall transformation and other initiatives to help ensure common stakeholder groups are understood and messages are appropriately sequenced, tailored, and bundled as necessary
Align key stakeholder groups to the communication plan
Engage leaders (Functional leads) to champion and cascade messages that resonate through all levels of the organisation.

## Slide 26
By engaging with the following identified stakeholders
CONFIDENTIAL
[Program Name] Version: Created By:
Stakeholder group | Internal | External | Project role
Steering Committee |  |  | Key cross functional advisors to the XX Project who will aid in steering the strategy and implementation of the new culture, process, policy and technology across the MDA. As leaders of the organisation and project sponsors, they will play a role in educating and building momentum and energy around the project.
Operations Committee |  |  | A leadership panel of advisors who act as champions of the XXX project; advisors are responsible for weighing in on key decisions and are often engaged in Steering Committee meetings
Service Area |  |  | A leadership panel of employees who must act as champions of the XXX project and new environment; they are responsible for weighing in on ongoing project decisions & risks.
Business Unit Owners |  |  | Project leadership responsible for making decisions, providing insight and direction at the workstream level
Workstream Leads |  |  | The ENTITY A individuals responsible for driving progress across each workstream
Core IT Team |  |  | Members of the immediate project team who are responsible for building the new environments, data management, identifying and raising risks and coordinating across work stream and function
Functional Leads |  |  | Leads of the organisational units who need to be engaged and updated to ensure consistent messaging and alignment from a programme level. Functional leaders will also be provided insight into new behaviours, processes, or technologies in advance of launch and prepped to message with employees correctly. These leaders play a critical role in identifying change network.
Change network nominees |  |  | Identified team members and employees who will develop two way communication channels with end users about the changes to culture, process, policy and technology ahead of time and help train and advocate program elements to others. These participants will be identified by the Functional leads . They are our key “on-the-ground” resources to affect change.
End - Users |  |  | xxxxxxx
XXX Core & Leadership Team
ILLUSTRATIVE EXAMPLE

## Slide 27
Develop a relevant communications strategy and plan
CONFIDENTIAL
[Program Name] Version: Created By:
Communications Plan
Change network
engagement and toolkits
Execution of communication
activities and toolkits
Feedback & measurement
Communications Strategy
Communications
Stakeholders will see similar material leveraged – more standardised communications
Leverage digital communication and collaboration tools to rapidly disseminate messages
Change networks engaged for feedback and continuous improvement.
Strategy
The communications and engagement strategy provides a framework for building commitment, which includes guidance for effective interventions. Interventions are the actual vehicles for developing stakeholder commitment and include traditional and non-traditional communications methods. The strategy helps to identify the types of interventions that help move stakeholders up the commitment curve
Process

## Slide 28
Utilising the core communication platform
CONFIDENTIAL
[Program Name] Version: Created By:
We are developing the XXX system to be xxx enablement tool which will support employees to do their job easier /
We are positioning a more effective and streamlined organisation by transforming the way we work.
Core message
Elevator pitch
Theme: Case for change
Theme: User benefits
Theme: Deployment
Theme: Challenges
The new xxx enablement platform will be released in MMM YYYY and will span across the following workstreams:
XXX
XXX
XXX
Single system
Out of the box capabilities
Reduced complexity
Personalised design
Streamlined processes
Enhanced data quality
Mobile and tablet access.
Highly complex, customised system
Too many ways to complete tasks from ambiguous and customised processes
Lack of mobile / on-the-go capabilities
Challenges in forecasting due to the delay of inputting data
Low data quality from unstructured and confusing input processes.
Theme: Key impacts
TBD
The level and number of stakeholder groups that must be involved
The degree of engagement required of these stakeholder groups.
Our transformation is enabling our GoJ-wide journey to redefine ourselves as a more efficient management organisation. Our transformation leverages new technologies that allow us to streamline our XXX processes and enhance data integrity. We will then prioritise future changes to enhance the new system to better meet our needs as we grow and develop as an organisation.

## Slide 29
Communication platforms to share information
CONFIDENTIAL
[Program Name] Version: Created By:
Functional leads in high impact areas will participate in roadshows
Rewards and recognition
High impact stakeholders and change network individuals
Ongoing pulse surveys
Intranet
Build excitement, share, benefits and engage
Project mailbox
FAQs built for various
functions, leaders and all end
users
Leadership videos
Celebrate project
releases with
leader featured videos
Ongoing engagement
and education on end user impacts and support structures
End User comms
End user specific
Communications, FAQs
SharePoint micro-site
Build out a Project Microsite
Change network
Showcases

## Slide 30
Strategies to engage the business and inspire adoption
CONFIDENTIAL
[Program Name] Version: Created By:
We will leverage the following:
Change network: Involves employees at various levels helping to prepare the organisation for change. Their advice, activities, and support increases the likelihood of engagement and ultimate success of the program
Two-way communication channels: Includes using the Change Network as the first tier of support, information & education between the project and end users. The Change Network will be one way we will capture ongoing two-way feedback from end users throughout the project.
Actions:
Leverage committed business champions to maximise levels of business engagement
Track business readiness to provide leadership with clear visibility and insight into how the program is progressing
Define clear accountabilities and regular readiness checkpoints to enable real time course correction for identified issues & risks.

## Slide 31
Developing a change network approach
CONFIDENTIAL
[Program Name] Version: Created By:
Executive Sponsors
Business Sponsors
Local Sponsors
Change Agents
& Champions
End User
Executive Sponsors
and drive a change.
Business Sponsors
have the
authority to legitimize and drive a
change for a particular region and/or
Business Unit.
Local Sponsors
have the authority,
responsibility, and credibility to
advocate and drive a change for a
particular site and/or function.
Bottom up communication
Sponsors
Change Advocates
Change Champions
End Users
Top Down Communication
Lateral communication on all levels
Sponsor XXX programme
Set the parameters for the change
Remove organisational barriers.
Advocate the change
Legitimise the change for the business
Facilitate the link between stakeholders.
Action the change
Assist advocates in championing the change
Act as a link to the local end-user community.
Provide expertise for their areas
Communicate with end-users
Serve as training, testing and support resources.
PERSON
PERSON
Steering Committee
Operations Committee
TBD
TBD
Customer Service representatives
Partners
Super Users
1
2
3
4

## Slide 32
Mobilise and engage the change network
CONFIDENTIAL
[Program Name] Version: Created By:
Outcome 1 Direct communication between leadership and frontline leaders
Outcome 3
Leadership behaviors extend to other front line leaders
Outcome 2 Influential front line leaders drive important initiatives
Enlist key stakeholders and develop work plans
Identify and validate champions and key behaviours
Kick-off champion network and report out key behaviours
Engage network in behavior spreading and key initiatives
Building the change network
1
2
3
4

## Slide 33
Method to prepare the organisation
CONFIDENTIAL
[Program Name] Version: Created By:
We will leverage the following:
Change impact analysis: An activity that will begin at the start of the transformation that provides a baseline of knowledge to help further refine the broader Change Plan. This plan will specify how and when the impacts would be addressed (e.g., communications, job aids, training, end-user support and processes). Based on the expected changes, the plan will include specific recommendations regarding any areas where communications and training activities may be required.
Actions:
Develop a change plan that clearly and accurately reflects how stakeholder groups will be impacted by the change
Provide relevant communications and training to impacted stakeholder groups. A key effort will be in identifying key personas and the processes which will change as a result of the XXX Transformation
Align company objectives with tangible incentives to drive behaviour change and adoption.

## Slide 34
Method to prepare the organisation
CONFIDENTIAL
[Program Name] Version: Created By:
  A change is a deviation from the current-state processes, systems, behaviours, and organisation structure
  An impact identifies how the changes affect specific parts of an organisation, an individual or an external entity.
  Findings are critical inputs to identify which types of change activities are best suited to help prepare and motivate stakeholders
  Provides a consolidated list of all identified changes and impacts of the program solutions.
  Assistance in identifying changes to people’s day-to-day tasks, overall process and procedures, technology and policies.
  Impact analysis across people, process and procedure and technology to inform stakeholder change plans, training plans and content, communication and change discussion guides.
  Overview
  Purpose
  Your role
  Outputs

## Slide 35
… and completing the change impact process to understand degree of impact by stakeholder
CONFIDENTIAL
[Program Name] Version: Created By:
  Validate change impacts
Group 3
…
…
...
Group 2
…
…
…
Group 1
…
…
…
Change Impacts
High
Medium
Low
People
…
…
...
Process
…
…
…
Technology
…
…
…

Process Leads compile known changes using change impact template Change impacts are identified throughout the process workshop as future processes are detailed Each impact is assessed as high, medium or low. | Impact types: People: Task or activity has been added to or taken away from a particular role Process: The order of tasks or activities has changed, or the activities described in the process are different Technology: The activities described in the process are performed using a technology different from that used today. | Validation is carried out with process leads Update change impacts Peer review impact assessments across process teams for content and impact accuracy and cross-process correlation. | Each impact is mapped to a stakeholder group The impact assessment by group is carried out by change team and validated with process areas. | Action planning will take place to assign change actions, responsibilities and timings for each impact Focus on high and medium impacts Actions are integrated to change management and communications plan.
Assess change impacts for each process area
Identified type of change impact
  Validate change impacts
Aggregated change impacts by Group
Planned change actions by Group

## Slide 36
Strategies to enable employees to new ways of working
CONFIDENTIAL
[Program Name] Version: Created By:
We will leverage the following:
Training strategy: Incorporates best practices to existing ENTITY A culture and capabilities
Training needs analysis: Refined for each deployment to understand the specific audience requirements and act as input to deployment specific Training Plans
Training plan: Incorporates the design, development and deployment of a blended learning solution.
Actions:
Design training to support critical change management and business readiness efforts
Prepare end users for go-live by increasing familiarity with the system, completing transactions, and institutionalising the new way of working.

## Slide 37
Developing a training strategy
CONFIDENTIAL
[Program Name] Version: Created By:
The training strategy conceptually defines the approach that will be taken to prepare ENTITY A
Key questions to cover in your strategy
Objectives
Scope & assumptions
Training needs & audience analysis
Approach
Development & execution
Timeline
Dependencies, risks & contingencies
What are the overall goals of the training?
Which target groups are in scope?
What content is included in the scope or excluded from the scope respectively?
What are underlying assumptions?
What are the characteristics of the stakeholder groups and which training needs have to be considered?
Which training components will be utilised to address the identified training needs?
Who will be involved in the training effort and how will roles and responsibilities be defined throughout the program? How will training be evaluated and maintained?
What are the foreseen timelines for the training development and execution?
What are known dependencies and risks and how can they be mitigated?

## Slide 38
Driving adoption through training and behaviour change
CONFIDENTIAL
[Program Name] Version: Created By:
Our training approach infuses blended learning into each project
Our training programmes will leverage existing tools and training templates to allow learners to learn in their own way and perform to a higher standard. Our programme incorporates the following:
  Role-based scenarios for instructor-led training and places learners in a real-world business setting
  Ample hands-on practice time to help build user proficiency through the use of walk-throughs and exercises
  Blended learning methods, interactivity, and creative learning activities centered around the end user to accommodate a variety of learning styles
  Training content delivered via e.g webinar, allowing ENTITY A the flexibility to accommodate changes that arise post go-live
  Extended practice sessions with activities and data tailored to identified personas
  Assesses knowledge and skills on an ongoing basis, allowing ENTITY A trainers and leaders the ability to provide necessary coaching, supplemental training, or job aides to enable employees to maintain high levels of performance.
  Extended practice sessions
  Role-based scenarios
  Ample hands-on practice time
  Blended learning methods
  Training content
  Assesses knowledge and skills
Blended
Learning Program

## Slide 39
Design, develop and pilot to end users
CONFIDENTIAL
Testing the training plan
Using impact analysis for each functional area, Training Lead pre-populates training needs analysis (TNA) template with initial mapping of activities to standard roles Training Lead incorporates information from Stakeholder Analysis and findings from Impact Assessments Training Lead populates course and module section with standard role-based training information. | Each Business Process Lead validates and completes the initial mapping of activities to standard roles in the Training Needs Analysis Mapping spreadsheet. | Further populate spreadsheet with information gathered during workshops/interviews regarding activity frequency, existing knowledge/skills, language considerations, work environment considerations, etc.. Revise TNA based on input from the business. | Meet with key stakeholders to validate the mapping and role-based curriculum Make any required updates and obtain sign-off from key stakeholders Training Lead creates TNA Executive Summary. | Refresh TNA in next program phase, as business process is further detailed and pilot scope/location is confirmed.
Create initial draft of training needs analysis (TNA) spreadsheet
Validate mapping
  Hold workshops/ interviews with the business; Revise TNA
Validate and sign-off TNA; Create summary
Refresh TNA in pilot phase



## Slide 40
Design, develop and pilot to end users
CONFIDENTIAL
[Program Name] Version: Created By:
Obtain
stakeholder
sign-off
Develop training materials
Review with stakeholders
Create evaluation
materials
Create training
Test plan
Create training and support maintenance plan
Perform final review
Select training tool
Prepare and educate team
on training templates
Create the necessary training materials that meet the learning objectives outlined in the training design
Ensure that these training materials are in line with end user needs as per the training needs analysis
Determine the required resources to test these materials, and ensure ongoing support of the training program post-roll-out
Testing the training plan

## Slide 41
How will we deploy the training plan?
CONFIDENTIAL
[Program Name] Version: Created By:
Leveraging internal resources to deliver the training programme
1
2
3
4
Pilot training materials with select employee groups (end users) and get feedback to refine training materials
Communicate training opportunities from key leadership and inform management to allow employees to take training
Leverage programme to distribute training to stakeholders in phases or waves
Conduct weekly knowledge checks and provide additional training opportunities if needed

## Slide 42
How will we ensure knowledge transfer
CONFIDENTIAL
[Program Name] Version: Created By:
We will leverage the following:
Knowledge transfer approach: Outlines how information will be transferred from the project team to key stakeholders within the organisation.
Knowledge transfer plan: A tracker which documents progress against knowledge transfer activities, timelines and key stakeholders.
Knowledge transfer summary: A high level summary of actions to date and next steps.
Actions:
Schedule monthly recurring meetings to socialise and share key information related to the transformation.
Arrange meetings between project leaders and individual stakeholder counterparts to socialise and share key documents and files.
Establishing a consistent process to share information with key stakeholders will be essential to preparing them for the change

## Slide 43
Align with key project stakeholders
CONFIDENTIAL
[Program Name] Version: Created By:
Leveraging a knowledge transfer approach that holds project leaders and stakeholders accountable
Identify Project Leaders and stakeholders
Develop knowledge transfer timeline & activities
Set expectations and conduct monthly handoff meetings
Summarise and share progress

## Slide 44
How we measure the effectiveness of the change programme
CONFIDENTIAL
[Program Name] Version: Created By:
We will leverage the following:
Change measurement approach: Uses specific measures and analytics to understand the dynamics between progress and change performance to help drive more consistent results and a tighter link to value. It will also focus on the timely assessment of change plans to determine effectiveness and to drive continuous improvements.
Actions:
Change is predictable; and can therefore be measured and managed
The measurement approach is comprehensive, data-driven, and lead to clear change actions and predictive insights
The measurement approach is integrated with the change plan to drive the day-to-day work of the project team.

## Slide 45
By measuring change progress
CONFIDENTIAL
[Program Name] Version: Created By:
Examples of quantitative go-live measures
Attendance/Engagement at steering committee meetings, trainings, and workshops
Current level of commitment by groups
Number of communications by type distributed across impacted stakeholders
Number of unique users who have logged into the system
Commitment level variance of functions groups
Number of communications distributed to function groups
Number of communications distributed to the change network
Attendance at change network events
Amount and type of feedback received

## Slide 46
Tracking and monitoring KPIs as we go
CONFIDENTIAL
[Program Name] Version: Created By:
Using the following KPIs for measuring success
Stakeholder awareness and understanding of the programme benefits and impacts
Employee engagement/ buy-in and participation measures
Use of training materials
Employee feedback
# of calls directed to Help Desk post go-live
Employee readiness assessment results
# of change network activities
# of change champions engaged
# of executives attending change meetings

## Slide 47: CONTACT US
TIU_Jamaica
TIU_Jamaica
TIUJamaica
www.publicsectortransformation.gov.jm
letusknow@transformation.gov.jm
Transformation Implementation Unit
Public Sector Transformation