## Slide 1
Business Readiness Plan Template

## Slide 2
Introduction
The business readiness plan is utilised by the project team to provide a visual high level guide of the key activities that need to be performed in order to prepare the organisation for the change that will be impact to the identified stakeholders within the MDA.
This document should be utilised along with the business readiness scorecard to outline all key activities that need to be performed.

## Slide 3
Business readiness plan
CONFIDENTIAL
ILLUSTRATION
 | Build | Test |  |  |  | Deploy |  |  | 
 | Nov. 20 | Dec. 20 | Jan. 21 | Feb. 21 | Mar. 21 | Apr. 21 | May 21 | Jun. 21 | July 21
BR / BE |  |  |  |  |  |  |  |  | 
Data & Cutover |  |  |  |  |  |  |  |  | 
R&I |  |  |  |  |  |  |  |  | 
GO LIVE
Leading the Change Workshops with Directors and Managers
Training Development
Course Design
Train the Trainer
Training Delivery
Scheduling & Logistics
Training Delivery Strategy
DRAFT BR DOC
FINALISE BR
EXECUTE BUSINESS RECONCILIATION (BR)
DR 1
DR 2
Cutover Simulation
Production Cutover
Reporting & Information: Support Business Readiness Validation
Detailed Design
SLAs & KPIs
BCM/BRV Approaches
Business Readiness Validation
BCM Testing
X/XX Agenda:
Review & Approve BRV Approach
Review high level function specific scorecard
Recommend Business representatives to work with business areas to finalize scorecard
Review BRV Approach
BR Scorecard - first draft
Refine & finalise scorecard
Business representatives (BRIG) work with business to finalize and validate scorecard
X/XX BRIG Agenda:
Validate BRV Scorecard
Sign off content
BRIG Agenda: Implement BRV approach
New system design approved
New system Fully
Operational
*
*
*

## Slide 4
Business readiness plan abbreviations
Abbreviations | Full title | Meaning
BR | Business readiness | Set of activities that are completed to support the organisation getting ready to transition to the change
BE | Business execution | Activities relating to the change required including training, comms etc.
R&I | Reporting and Information | Reporting approach used to validate if the organisation is ready to execute the transition to the new state
BCM | Business continuity management | A contingency plan if the transition does not work
BRV | Business readiness validation | Checklist and survey used to assess if the organisation is ready to execute the transition to the new state
BRIG | Business readiness implementation group | A team of selected senior people from MDA organisation and project with technical understanding of the change, who will support validation and recommend go / no go decisions
DR | Data reconciliation | A new system will validate its data against a set of criteria to ensure it is compliant with the business rules
SLA | Service level agreement | Used to create a benchmark standard for operating a business process
KPI | Key performance indicator | Used as a measurement of the benchmark for a service level agreement

## Slide 5: CONTACT US
TIU_Jamaica
TIU_Jamaica
TIUJamaica
www.publicsectortransformation.gov.jm
letusknow@transformation.gov.jm
Transformation Implementation Unit
Public Sector Transformation